# Logical framework

Data will be disaggregated by gender, vulnerability and geographical location, and any other relevant disaggregation as required.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Intervention logic** | **Indicators** | **Source of baseline data** | **Target** | **Sources of verification** | **Assumption** |
| **OUTCOME** |
| **Specific Objective:** Young women and men are better equipped to access inclusive and decent employment opportunities | % of beneficiary youth absorbed in the labour market six months after completing a training programme (result 1 and 2) (disaggregated per sex, vulnerability and region) |  Tracer study, (beneficiaries registrar) | 80% beneficiary youth participating in programmes under result 1 and 2 absorbed in the labour market by end of 2024 | Tracer studyAction research | Politic and macro-economic stability of the country and the regionSufficient private sector companies capable to retain or employ beneficiary youth (results 1 and 2) |
| % of beneficiary youth participating in the First Employment Facility and up- and reskilling training programmes obtain a recognized certificate (disaggregated per sex and region) |  N/A  | 90% beneficiary youth certified by mid-2024 |  Monitoring reportsAssessment reportsTracer study | The accreditation system governed by the Ministry of Labour can provide licensing |
| Implementing partners provide services promoting inclusion of vulnerable youth, including youth women  | N/A | All grant agreements integrate at least two services promoting social inclusion | Action research | The stakeholders involved in implementation are willing to collaborate on identification of standards, and development of the assessment |
| **OUTPUT** |
| **Output 2:** Young women and men are equipped with demand-driven, quality skills | # of curricula developed or upgraded  | N/A | 15 curricula developed or upgraded and accredited by end of 2022 | Monitoring reportsAccreditation | The private sector actors and TVET providers involved in the implementation are willing to collaborateLocalities hosting innovation hubs are interested to extend grant agreements initiated under *Skilled Young Palestine* interventionSufficient youth graduates and workers are# willing to participate in the training programmesCommunities support graduates’ participation |
| # of trainers trained on new or upgraded curricula  | N/A | 30 trainers trained by Q2, 2023 | Monitoring and training reports |
| # of youth graduates and workers participating in up- and reskilling programmes (disaggregated per sex, vulnerability and region) | N/A | 450 (incl 50% vulnerable youth and 40% youth women) have participated in training by mid-2024 | Monitoring and training reports  |