## SUMMARY
WEZESHA BINTI PROJECT - 2 DOMITORIES AND 8 WASH FACILITIES AT KASULU TC &DC
Date:
REVISED SUMMARY
S/N | Item | Unit | Qnt | Unit Cost | Total
1 | 120 Girl's Dormitory- Ntamya sec school - Kasulu DC | Nos | 1 | 0 | 0
2 | 84 Girl's Dormitory - Mwanga sec school Kasulu TC | Nos | 1 | 0 | 0
3 | Renovation of Mwanga WASH facility | Nos | 1 | 0 | 0
4 | WASH Facilities - | Nos | 9 | 0 | 0
TOTAL(EUR) |  |  |  |  | 0

## 84 Girls Dormitoryn -Mwanga sec
Bill of Quantities For the Construction of 120 girls dormitory at Kidahwe secondary school -Kigoma MC
S/No | Item | Unit | Qnt | Rate | Total
1 | PRELIMINARIES AND GENERAL COST
A | The Contractor shall be deemed to have visited the site and satisfied himself as to:- The nature of the site, The amount of bush, rubbish or debris to be cleared away before commencement, access to the site, availability of materials and the like. All the cost is for contractor |  |  | NA | NA
B | Allawance for material testing | Item | 1 |  | 0
0
C | Secure performance bond and insurance | Item | 1 |  | 0
D | Preparation of as built drawings | Item | 1 |  | 0
E | Mobilization and demobilization of tools, materials, manpower, and equipment. | Item | 1 |  | 0 |  | 0.6 | 0.6
[7 empty] | 0.6 | 0 | area for 120 | 33
F | Signboard and project registration | Item | 1 |  | 0 |  | 0.6 | 0.6 | Area for 84 | 23
G | Site Clearance: Removing bushes, shrubs, trees, etc. Clearing the site carefully without exceeding damaging tree near the constuction site; grubbing up roots bushes, shrub, undergrowth or the like; and removing all bushes surplus soil away keep clean for receiving materials | Item | 1 |  | 0 |  | 0.6 | 0.6 | defference | 10
H | Water for the works: The contractor shall allow for all necessary clean fresh water for the works, including that required by sub-contractors and for any temporary plumbing meters and storage facilities and pay all charges in connection therewith and clear away on completion and make good works disturbed. | Item | 1 |  | 0
[7 empty] | 0.6 | 0 | 84 is less than 120 by | 0.43478
I | Store and engineers office Supply and Construct temporary store for workers, engineer's office and materials to ensure proper storage of cement on raised floor with timbers and prevention of moisture is maintained . | Ls | 1 |  | 0 |  | 0.6 | 0.6 | factor the120 to get 50 by | 0.56522
[7 empty] | 0.6 | 0
| SUB-TOTAL Emelement no 1: preliminaries |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
2 | SETTING OUT AND FOUNDATION | [5 empty] | 0.6 | 0
| Item | Unit | Qnt | Rate | Total |  | 0.6 | #VALUE!
[7 empty] | 0.6 | 0 | Area for 84 | 990
| Excavation | [5 empty] | 0.6 | 0 | Area for 120 | 1868.16
A | average 100 mm deep; to remove vegetable soil | m3 | 121.5 |  | 0 | 0 | 0.6 | 72.9 | difference | 878.16
B | Removing away from the site excavated material | m3 | 121.5 |  | 0 |  | 0.6 | 72.9 | 84 is less than 120 by | 0.88703
C | Excavate foundation trenches to commencing walling | m3 | 352 |  | 0 |  | 0.6 | 211.2
[5 empty] | 0 |  | 0.6 | 0
| Setting out and Foundation masonry |  |  |  | 0 |  | 0.6 | 0
[5 empty] | 0 |  | 0.6 | 0
D | Dewatering Keeping excavations free from all water including spring and running water | Ls | 1 |  | 0 |  | 0.6 | 0.6
[7 empty] | 0.6 | 0
E | Stone masonry Foundation 600mm stone masonry wall: Mortar mixing ratio is 1:3 use 42.5N/mm2 cement strength Use big stones at least 40cm, hard, roughed surface texture, non round stones. Put big regular stone at conners. All stones are laid flat, all courses must alternate (zig zag) to prevent straight joint. Chop out rust layer around stone and clean with brush and water. Sett all dimensions as per drawing. Apply mortar to all joints close gaps with small stones. (Includes stairs and ramps) | m3 | 271.3 |  | 0 |  | 0.6 | 162.78
F | Backfilling Fill excavated soil from foundation treches ,compact in layers of 0.15cm and consolidate around foundation to achieve 98% maximum dry density (M.D.D) | m3 | 206.3 |  | 0 |  | 0.6 | 123.78
G | Hardcore 200 mm thick bed; levelled; compacted and blinded to receive polythene membrane; membrane; measured separately | m2 | 365 |  | 0 |  | 0.6 | 219
H | DPM Supply and lay 1000 gauge polythene Damp Proofing Membrane (with 150mm laps) over the sand blended into hardcores | M2 | 365 |  | 0 |  | 0.6 | 219
I | Anti-Termite ApplyTermite Killer; solution at the rate of 7 litres per square metre to hardcore beds | M2 | 365 |  | 0 |  | 0.6 | 219
J | Oversite conrete slab (1:3:6) Supply and pour plain concrete for oversite slab batched by volume a mixing ratio of 1:3:6 | M3 | 84 |  | 0 |  | 0.6 | 50.4
[7 empty] | 0.6 | 0
| RAMPS and STEPS (total of 7 ramps) | [5 empty] | 0.6 | 0
K | Foundation: Construct a 300mm thick stone masonry wall | m3 | 39.7 |  | 0 |  | 0.6 | 23.82
L | 400 mm thick hard core | m2 | 32 |  | 0 |  | 0.6 | 19.2
M | 100 mm thick, Plain concrete slab grade 15 | m2 | 32 |  | 0 |  | 0.6 | 19.2
[7 empty] | 0.6 | 0
| SUB-TOTAL ELEMEMNT No 2 - SUBSTRUCTURE |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
3 | ELEMENT No2: SUPERSTRUCTURE WALLS | [5 empty] | 0.6 | 0
| Item | Unit | Qnt | Rate | Total |  | 0.6 | #VALUE!
A | DPC 350mm wide horizontal bituminous hessian base damp proof course laid on oversite concrete with 150mm laps beds ready to receive ISSB walls. | m | 214 |  | 0 |  | 0.6 | 128.4
[7 empty] | 0.6 | 0
| EXTERNAL AND INTERNAL WALLING | [5 empty] | 0.6 | 0
B | Solid 230mm Thick hydraform walling external and internal walls, cost to include extraction and preparation of soil, block fabrication, curing and installation (with the strength of 3-5 MPa) | M2 | 755.96 |  | 0 |  | 0.6 | 453.576
C | 750 mm high Perforated bricks wall, 230mm Thick hydraform external walling. Cost to include extraction and preparation of soil, block fabrication, curing and installation (with the strength of 3-5 MPa) | m2 | 95 |  | 0 |  | 0.6 | 57
CONCRETE WORK:
Reinforced insitu concrete grade ‘15’ including vibrating around reinforcements.
D | Horizontal ring beams | M3 | 24 |  | 0
| High tensile steel bar reinforcement to BS 4449:1997, including cutting to length, bending, hoisting and fixing and all necessary tying wires and spacing blocks | [5 empty] | 0.6 | 0
E | 12mm diameter | Kgs | 1244 |  | 0
F | 8mm diameter | Kgs | 356 |  | 0
| FORMWORK TO INSITU CONCRETE | [5 empty] | 0.6 | 0
| Sides,Vertical or Battering | [5 empty] | 0.6 | 0
G | Supply, fix formworks and ormworks removal, including all tools and materials needed for preparation and installation | M2 | 210 |  | 0 |  | 0.6 | #REF!
H | Supply and cast 75mm diameter black pipe poles to suport roof at veranda. Use conrete grade 20 to cast it. | Nos | 15 |  | 0
[7 empty] | 0.6 | 0
| TOTAL ELEMENT NO 3: SUPERSTRUCTURE - Walls and Frames |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
4 | Roofing and water havesting | [5 empty] | 0.6 | 0
| Roof structure | [5 empty] | 0.6 | 0
[7 empty] | 0.6 | 0
A | Truss Fabrication and Installation • Materials: Supply well-seasoned and treated timber. Timber sections to be used:  Rafters: 50x150 mm. - eucaliptus  Tie beams: 50x150 mm. eucaliptus  Wall plates and struts: 50x100 mm. eucaliptus  Purlins: 50x70 mm. - Pine soft wood timber • Fabrication: Fabricate the trusses as per the provided drawings. Ensure the trusses are fabricated with a rafter slope of 8 degrees. • Installation: Install the fabricated trusses on the ring beam with a spacing of 1.4 meters center-to-center (c/c). Anchor the trusses to the ring beam using core M6 steel bars casted in the ring beam. Use two bolts (12mm diameter) with nuts and 2inches diameter washers to secure the joints of rafters and tie beams. • Overhangs: o The external overhang is to be 1.5 meters long. o The internal overhang at the hallway is to be 0.8 meters long. • Additional Provisions: o All tools, nails, and materials necessary for the truss fabrication and installation are to be included | Nos | 94 |  | 0 |  | 0.6 | 56.4
B | Supply and fix 28 gaurge IT5 colorless but not transparant covering sheets, fixed on streated pine timber purlins with rubbered roofing nails of 3.5 inches length | m2 | 700.58 |  | 0 |  | 0.6 | 420.348
C | Supply and fix a Fascia board: use well seasoned and treated pine timber - 25x200mm. fix brackets with screw of a lenght of 1.5 inches , fixed at 600mm c/c | m | 44.63 |  | 0 |  | 0.6 | 26.778
D | Valley cap, 450mm girth | LM | 93 |  | 0
E | supply a micro coffee mesh wire and fix it behind the perforated fill masonry wall on top of ring beam to prevent dust from entering the top of the ceiling. Further instruction to e given by engineer on site. | m2 | 63.16 |  | 0 |  | 0.6 | 37.896
[7 empty] | 0.6 | 0
F | Optional quantity for modifications or expansion of the roof in public space: Supply and install a complete steel roof truss structure plus IT5 roof covering. | m2 | 28.8 |  | 0 |  | 0.6 | 17.28
G | Ceiling Supply and install 50x50 mm treated pine timber brandering, plain gypsum conices, and fix 9mm thick gypsum board as per Thailand or the like. | m3 | 397.14 |  | 0
[7 empty] | 0.6 | 0
| Water harvesting systeam | [5 empty] | 0.6 | 0
H | Gutters Supply and fix class B PVC gutter 150mm diameter by 75mm deep. Including 75mm downpipes, 500mm c/c brackets, plus all required fittings and glues. | m | 177.3 |  | 0 |  | 0.6 | 106.38
I | Storrage poly tanks Supply and install 4 sim tanks of 5,000 litres each and build a ground base of stone masonry post with atwo crossing walls at the middle 600mm high from the ground, 700mm deep, 500mm width, 180mm diameter, 150mm thick concrete grade 20 with 6mm BRC. | Nos | 4 |  | 0 |  | 0.6 | 2.4
[7 empty] | 0.6 | 0
| TOTAL ELEMENT No 4: ROOFING AND RAIN WATER HARVESTING |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
5 | FINISHING | [5 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  | 0.6 | #VALUE!
| Plastering | [5 empty] | 0.6 | 0
A | External wall: foundation Pointing a stone masonry foundation wall the size of the pointing is 25mm thick same for depth mixiting ratio is 1:3 cement sand | m2 | 91.87 |  | 0 |  | 0.6 | 55.122
B | External wall: superstructure Plaster 1:3 cement sand, 25mm thick 0.5m high from DPC level | m2 | 130 |  | 0 |  | 0.6 | 78
C | Externally: apply a 25mm thick Plaster 1:4 cement sand to all beams, and corners of the walls and around windows a strip of 75mm wide | m2 | 83.16 |  | 0 |  | 0.6 | 49.896
[5 empty] | 0 |  | 0.6 | 0
| Internal walls finishing (1:4) |  |  |  | 0 |  | 0.6 | 0
D | Plastering 25mm thick to obtain a smooth finish then skim with lime. | m2 | 784.99 |  | 0 |  | 0.6 | 470.994
[5 empty] | 0 |  | 0.6 | 0
| Floor finishing |  |  |  | 0 |  | 0.6 | 0
E | Supply and cast a Terrazzo floor finish including 150mm high skirtings | m2 | 397.14 |  | 0 |  | 0.6 | 238.284
[5 empty] | 0 |  | 0.6 | 0
| Painting and decoration works |  |  |  | 0 |  | 0.6 | 0
| Externally |  |  |  | 0 |  | 0.6 | 0
F | Clean and apply three coat of seed oil or apply a varnish to all ISSB external walls | m2 | 436.25 |  | 0 |  | 0.6 | 261.75
G | Supply and Skimming to obtain a smooth finish, clean, prime and Apply water-based weather guard paint to all plastered columns and beams and windows | m2 | 83.16 |  | 0 |  | 0.6 | 49.896
[5 empty] | 0 |  | 0.6 | 0
| Internally: supply,skim,clean and apply |  |  |  | 0 |  | 0.6 | 0
H | Emulsion Painting to internal wall surfaces | m2 | 784.99 |  | 0 |  | 0.6 | 470.994
I | Emulsion Painting to Celling (rooms and verandah | m2 | 341.7 |  | 0 |  | 0.6 | 205.02
J | Oil-based painting fascia board | m2 | 44.63 |  | 0 |  | 0.6 | 26.778
[7 empty] | 0.6 | 0
| SUB-TOTAL ELEMENT No 5- FINISHING |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
6 | ELECTRICAL INSTALLATION | [5 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  | 0.6 | #VALUE!
| Electrical Installation (ABB or Tronic standard): Electricity wiring and connection to powerline without buying an electrical poles: Installing wiring and electrical equipment as per drawing | [5 empty] | 0.6 | 0
A | Energy saver LED BULB Complete with straight Complete, Use single core wires pure copper, double eath rod approved pure copper 16sqmm each. NB: Cables for 1.5sqmm 2.5sqmm, 4sqmm, 6sqmm, 10sqmm should be EURO or other equal approved | Sum | 1 |  | 0 |  | 0.6 | 0.6
[7 empty] | 0.6 | 0
| TOTAL ELEMENT No 6: ELECTRICITY INSTALLATION |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
7 | DOORS FRAME AND SHUTTER | [5 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  | 0.6 | #VALUE!
| Doors Shutter Prime quality hardwood paneled doors mninga or other equal and approved hardwood 45mm Thick panelled single door Mahogany timber finish, comprising of 45 x 150mm top and middle rails, 45 x 150mm stiles and 45 x 200 bottom rail, panels filled in with and including 35mm thick moulded boarding tongued and grooved all round rails Including Supply and fix the following "UNION" make or other equal and approved iron-mongery To softwood, hardwood or the like; fixing with screws ;- 3-Lever Mortise lock with furniture, Toiles and Bathroom lock with indicating bolt, 100mm Brass butt hinges | [5 empty] | 0.6 | 0
A | Ditto 900 x 2100mm high. | No | 19 |  | 0 |  | 0.6 | 11.4
| Supply and install Metal gates/doors | [5 empty] | 0.6 | 0
B | 1500x2100mm high ( for main exits gates) | Nos | 4 |  | 0 |  | 0.6 | 2.4
C | (Optional item) Supply and fix metal grills for fixing oppenings at the puplic space/common room , size of grills is 7mx2m high, | M2 | 14 |  | 0
| Supply and fix Door frames: Hardwood mininga or other equal and approved hardwood. Provide 16mm diameter burglar bars 150mm c/c , fix perforated 5mm thick clear sheet glass glazed to hardwood frame with glazing beads and fix a clear mosiquito wire net to prevent dust ant insects. | [5 empty] | 0.6 | 0
D | Ditto 950x2800mm high | Nos | 23 |  | 0 |  | 0.6 | 13.8
[7 empty] | 0.6 | 0
[7 empty] | 0.6 | 0
| TOTAL ELEMENT NO 7: DOORS |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
8 | Windows | [5 empty] | 0.6 | 0
| Supply and fix metal windows with openable grills fix with tinted glass glazing, perforated ventilation with clear glass glazing, and two sliding panels fixed with mosquitor wire net. Use 25x50mm hallow section steel stiles, 38x38mm HS grills, 25x25mm angle line steel for glazing, Inclding all iron mongeries | [5 empty] | 0.6 | 0
A | Ditto 1500x2000mm High | Nos | 23 |  | 0 |  | 0.6 | 13.8
[7 empty] | 0.6 | 0
| TOTAL ELEMENT NO 8: WINDOWS |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
9 | EQUIPMENT | [5 empty] | 0.6 | 0
| FIRE FIGHTING INSTALLATION | [5 empty] | 0.6 | 0
A | Supply and install 9KG, dry powder 'NAFFCO' or 'ANGUS' any other equal and approved fire extinguishers | Nos | 4 |  | 0 |  | 0.6 | 2.4
B | Stand alone smoke detector | Nos | 7 |  | 0 |  | 0.6 | 4.2
[7 empty] | 0.6 | 0
9 | TROTAL ELEMENT NO 9: FIRE FIGHITING EQUIPLENTS |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
SUB SUMMARY DORMITORY ROOMS | [6 empty] | 0.6 | 0
1 | SUB-TOTAL Emelement no 1: preliminaries |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
2 | SUB-TOTAL ELEMEMNT No 2 - SUBSTRUCTURE |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
3 | TOTAL ELEMENT NO 3: SUPERSTRUCTURE - Walls and Frames |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
4 | TOTAL ELEMENT No 4: ROOFING AND RAIN WATER HARVESTING |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
5 | SUB-TOTAL ELEMENT No 5- FINISHING |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
6 | ELECTRICAL INSTALLATION |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
7 | TOTAL ELEMENT NO 7: DOORS |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
8 | TOTAL ELEMENT NO 8: WINDOWS |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
9 | TROTAL ELEMENT NO 9: FIRE FIGHITING EQUIPLENTS |  |  |  | 0 |  | 0.6 | 0
[7 empty] | 0.6 | 0
| SUM FOR 84 GIRL'S DORMITORY |  |  |  | 0 |  | 0.6 | 0
TOILETS and LAUNDRY
1 | Foundation and walling
A | Site cleance and excavation of foundations | m3 | 41 |  | 0
B | Foundation masonry stone walls 1:3 | m3 | 43 |  | 0
C | Plain Oversite conrete 1:3:6, DPM first | m2 | 72 |  | 0
D | Supply and cast 75mm diameter black pipe poles to suport roof at veranda. Use conrete grade 20 to cast it. | Nos | 2 |  | 0
E | Walling using ISSB blocks,on DPC | m2 | 157.82 |  | 0
CONCRETE WORK:
Reinforced insitu concrete grade ‘15’ including vibrating around reinforcements.
D | Concrete | M3 | 2.3 |  | 0
| High tensile steel bar reinforcement to BS 4449:1997, including cutting to length, bending, hoisting and fixing and all necessary tying wires and spacing blocks | [5 empty] | 0.6 | 0
E | 12mm diameter | Kgs | 150 |  | 0
F | 8mm diameter including binding wire | Kgs | 82 |  | 0
| M6 bars for truss arnchoring, to be casted with ring beams and potrudes out of conrete by 400mm length | Kgs | 30 |  | 0
| FORMWORK TO INSITU CONCRETE | [5 empty] | 0.6 | 0
| Sides,Vertical or Battering | [5 empty] | 0.6 | 0
G | Supply, fix formworks and formworks removal, including all tools and materials needed for preparation and installation | M2 | 25 |  | 0 |  | 0.6 | #REF!
| TOTAL FOUNDATION AND WALLING |  |  |  | 0
2 | Roof structure
A | Truss Fabrication and Installation • Materials: Supply well-seasoned and treated timber. Timber sections to be used:  Rafters: 50x150 mm. - eucaliptus  Tie beams: 50x150 mm. eucaliptus  Wall plates and struts: 50x100 mm. eucaliptus  Purlins: 50x70 mm. - Pine soft wood timber • Fabrication: Fabricate the trusses as per the provided drawings. Ensure the trusses are fabricated with a rafter slope of 8 degrees. • Installation: Install the fabricated trusses on the ring beam with a spacing of 1.4 meters center-to-center (c/c). Anchor the trusses to the ring beam using core M6 steel bars casted in the ring beam. Use two bolts (12mm diameter) with nuts and 2inches diameter washers to secure the joints of rafters and tie beams. • Overhangs: o The external overhang is to be 1.5 meters long. o The internal overhang at the hallway is to be 0.8 meters long. • Additional Provisions: o All tools, nails, and materials necessary for the truss fabrication and installation are to be included | Nos | 9 |  | 0 |  | 0.6 | 5.4
G | Purlins- treated Pine timber 50x75mm | m | 65.1 |  | 0
H | IT5 colorless but not trasperant covering sheets, fixed on streated pine timber purlins with roofing nails of 3.5 inches length | m2 | 137 |  | 0
I | Fascia board: treated pine timber - 25x200mm. fix brackets with srews 1.5cm long, brackets to be spaced at 600mm c/c | m | 30.1 |  | 0
0
| TOTAL ROOFING |  |  |  | 0
3 | RC Concrete dhobi sinks |  |  |  | 0
A | Construct a (1:2:4) 6mm BRC reinforced concrete wash basin with a 600mm x 400mm width by 350mm depth internal dimension, and provide a 50mm diameter water outlet hole provided with trap and screener, 100mm concrete partition wall between one wash basin to another same for slab. Top-level of wash basin from floor is 750mm, it will be casted on top of brick wall, includes formworks, bottle trap, drainers and necessary accessories; ( it will be used as hand wash basin as well) | m3 | 3.2 |  | 0
| TOTAL DHOBI SINKS |  |  |  | 0
4 | DOORS
Doors Shutter Prime quality hardwood paneled doors mninga or other equal and approved hardwood 45mm Thick panelled single door Mahogany timber finish, comprising of 45 x 150mm top and middle rails, 45 x 150mm stiles and 45 x 200 bottom rail, panels filled in with and including 35mm thick moulded boarding tongued and grooved all round rails Including Supply and fix the following "UNION" make or other equal and approved iron-mongery To softwood, hardwood or the like; fixing with screws ;- 3-Lever Mortise lock with furniture, Toiles and Bathroom lock with indicating bolt, 100mm Brass butt hinges
A | Ditto 800 x 2000mm high. ( toilets and changing room) | No | 11 |  | 0
B | Ditto 1000 x 2000mm high, provide with 900mm door handle , double swing hinges to open inward and outward swing. PWD | No | 1 |  | 0
C | Metal door 900x2000mm high ( at incinerator area) | Nos | 1 |  | 0
Supply and fix Door frames: Hardwood mininga or other equal and approved hardwood. Provide 16mm diameter burglar bars 150mm c/c , fix perforated 5mm thick clear sheet glass glazed to hardwood frame with glazing beads and fix a clear mosiquito wire net to prevent dust ant insects.
D | Ditto 850x2800mm high (Changing room and incinerator) | Nos | 2 |  | 0
E | 850x2000mm , high no vents, no glass, no buglar bars ( for Toilets) | Nos | 10 |  | 0
F | 1050x2000mm high no vents, no glass, no buglar bars ( for Toilets-PWD) | Nos | 1 |  | 0
| TOTAL DOORS |  |  |  | 0
5 | Windows
A | Ditto1000x600 High ( Toilet) | Nos | 10 |  | 0
| TOTAL WINDOW |  |  |  | 0
6 | Finishing
A | Plastering 25mm thick 1:3 cement sand to foundation wall and to internal walls | m2 | 117.18 |  | 0
B | water proof plaster in inernal toilet walls and terrazzo to laundry and above wash basin | m2 | 69.16 |  | 0
C | Terrazzo floor incl 150mm high skirtings | m2 | 91 |  | 0
D | Vanish exernal ISSB wall | m2 | 80.29 |  | 0
E | Painting three coats of bituminous paint to foundation walls, internal walls and to beams, painting red oxide to trusses and fascia board | m2 | 31.08 |  | 0
| TOTAL FINISHING |  |  |  | 0
7 | Plumbing and Sanitary Installation
Supply and install and test ;
A | Wash hand basins; white vitreous China; 32mm chromium plated chain waste 32mm plastic bottle trap concealed bracket with fixing clamps pair 12mm pillar taps 420 x 510mm; requiring plugging. fixing with brass screws to backgrounds ( install at changing/women's room and at disabled toilet room) | Nos | 2 |  | 0
B | Squatting -White vitreous asian type W.C suite comprising 9 litres capacity cistern with cover, 12mm BSS high pressure ball valve, plastic syphon fitting, side supply and overflow set | Nos | 6 |  | 0
C | Complete disabled toilets, grab rails, mixer, floor drainer and all nesessary accessories | Nos | 1 |  | 0
D | 80mm Diameter high quality plastic floor drain trap built in concrete bed | Nos | 6 |  | 0
E | 6mm silver mirror, lead backed, size 450 x600mm with arise edges fixed to wall with mirror screws | Nos | 4 |  | 0
F | 20mmØ Chromium plated towel single rail, 600mm long | Nos | 5 |  | 0
G | 100mm long soap holder (PVC), plugged and screwed to brick wall | Nos | 5 |  | 0
H | Shurtuff (Douche spray) 13mm diameter X 1000mm long flexible hose metal braided hose | Nos | 8 |  | 0
I
J | Pipes work in building
K | A: Supply pipe PN 16
L | 25mmØ communication pipe HDPE to trench | m | 31.5 |  | 0
M | Ditto; tee | Nos | 12 |  | 0
N | Ditto; elbow | Nos | 18 |  | 0
O | Ditto; male connector | Nos | 12 |  | 0
P | 32mmØ pipe to trench | Nos | 23 |  | 0
Q | Ditto; elbow | Nos | 5 |  | 0
R | Ditto; nipple MM | Nos | 18 |  | 0
S | Ditto; nipple FF | Nos | 18 |  | 0
T | Ditto; union | Nos | 13 |  | 0
U | Ditto; reducing connector 32Ø × 25Ø | Nos | 19 |  | 0
V | Ditto; reducing connector 25Ø × 19Ø | Nos | 19 |  | 0
W | Ditto; nipple MM | Nos | 19 |  | 0
X | Ditto; reducing connector 19Ø × 13Ø | Nos | 19 |  | 0
Y | 13mm diameter pipe in blockwall chase BS 1010 or 1212 | m | 32 |  | 0
Z | Ditto; elbow | Nos | 39 |  | 0
AA | Ditto; tee. | Nos | 20 |  | 0
AB | Ditto: nipple MM | Nos | 20 |  | 0
AC | Ditto: nipple FF | Nos | 20 |  | 0
AD | Ditto: union | Nos | 20 |  | 0
B: WASTE AND VENT PIPES
UPVC pipes: class 'C'
AE | 38mmØ; chase in block in concrete slab. | m | 20 |  | 0
AF | Ditto: Equal tee | Nos | 10 |  | 0
AG | Ditto; plain elbow | Nos | 6 |  | 0
AH | Ditto; plugged elbow |  | 6 |  | 0
AI | C: SOIL AND PIPES
AJ | UPVC pipes and fittings: Class 'C'
AK | 100mmØ pipe fixed to walls | m | 9 |  | 0
AL | Ditto; laid in trenches. | m | 32 |  | 0
AM | Ditto; plugged bend 90˚. | Nos | 10 |  | 0
AN | Ditto; plain bend 90˚. | Nos | 10 |  | 0
D: Ancillaries:
Draw off taps; stop valves; copper alloy to BS 5154 or BS 1010
AO | 13mmØ stop valve | Nos | 21 |  | 0
AP | 13mm Ø bib taps Chrome plated | Nos | 21 |  | 0
AQ | 13mm angle valves | Nos | 8 |  | 0
AR | Provision for wastebin for waste collection in the MHM room | Nos | 2 |  | 0
FOUL WATER DRAINAGE
MANHOLE AND GULLY TRAP
AS | Construct a masonry manhole size 600 x x600mm average depth 600mm with fired bricks, mortar ratio 1:3 | Nos | 7 |  | 0
AT | Construct a standard gully trap chambers with internal dimensions of 300x300mm by 300mm deep using burnt bricks | Nos | 10 |  | 0
0
0
| Soak way pit |  |  |  | 0
AU | Construct complete soak away pit, size 3m diam with 3.5m depth, including excavation, perforated brick wall, pipe 4" connection, vent pipe 4",Y12 150 C/C top and bottom face reinforced concrete slab 150mm thick, formwork, precast concrete cover 450 x 450mm | LS | 1 |  | 0
0
Septic Tank
AV | Allow for construction of faul water septic tank of internal dimension 5000Lx2000Wx3000D mm, of capacity 17,280Litres complete , Y12 150 c/c bottom face reinforced concrete grade 20 , formwork and other associated accessories | LS | 1 |  | 0
| TOTAL PLUMBING AND SANITARY ISTALLATION |  |  |  | 0
SUB SUMMARY - TOILET
| Foundation and walling |  |  |  | 0
| Roof structure |  |  |  | 0
| Finishing |  |  |  | 0
| Plumbing and Sanitary Installation |  |  |  | 0
| SUM TOILET AND LAUNDRY |  |  |  | 0
8 | WATER TOWER
A | Site cleance and excavation of foundations | m3 | 13 |  | 0
B | Masonry foundation wall | m2 | 46 |  | 0
C | 300mm thick Walling with fired bricks | m2 | 140 |  | 0
D | Supply and cast concrete grade 15 for oversite concrete | m2 | 28 |  | 0
E | RC concrete beams 4Y12 main bars, Y8-200c/c stirups, formworks | m3 | 1 |  | 0
F | RC concrete beams 4Y16 main bars, Y8-200c/c stirups, formworks. | M3 | 0.44 |  | 0
G | RC conrete roof slab mix ratio 1:2:4, Y12-175 c/c- use cement 42.5Nmm2 , formworks | m3 | 1.29 |  | 0
H | Construct four (4) reinforced concrete columns, column footings 4Y12 main bars, Y8-200c/c stirups, formworks. | m3 | 3 |  | 0
I | Plastering and skiming with lime ( optional) | m2 | 35 |  | 0
J | Painting ( optional) | m2 | 35 |  | 0
K | Supply and install 1000x2500 metal door with all accessories including padlocks for the store. | Nos | 1 |  | 0
L | Supply and install a sim tanks of 10,000 litres at top of the tower | Nos | 1 |  | 0
M | Supply and install a sim tanks of 5,000 litres at ground build foundation base | Nos | 1 |  | 0
| TOTAL WATER TOWER |  |  |  | 0
9 | INCINERATOR
A | Excavations | m3 | 2.5 |  | 0
B | Masonry stone foundation wall , motar 1:3 cement sand | m3 | 2.03 |  | 0
C | Fired brick 230mm walls 980x780mm internally by | m2 | 9.152 |  | 0
D | concrete grade 20 (1:2:4) reinforced 6mm BRC | m3 | 0.254 |  | 0
E | Reinforcement Y16 for burning platform | Kgs | 36.4 |  | 0
F | 150mm thick fired brick walls for 4.6m chimney jointed with cement mortar 1:3 | m2 | 4.214 |  | 0
Finishing
G | Pointing works and Panting works to ring beam surface color to be directed by the clien | m2 | 19.5 |  | 0
H | W3 - 400x400mm metal window for collecting ashes and inserting fuel into a burning chamber | Nos | 1 |  | 0
I | W4 - 300X300mm waste inlet window | Nos | 1 |  | 0
| TOTAL INCINERATOR |  |  |  | 0
10 | FENCE
A | Excavations of foundation | m3 | 4 |  | 0
B | Stone masonry foundation wall 500mm high from ground level , mortar 1:3 cement sand | m3 | 8 |  | 0
C | 230mm thick ISSB walling on DPC . a height of 1.4m will be solid and top portion of 1.6m will be perforated | m2 | 27 |  | 0
D | RC concrete beam at 1.8m from DPC LEVEL , c.rario 1:2:4 with 4Y12 and Y8-200C/C, including formworks. | m3 | 1 |  | 0
E | 6mm BRC, 1:2:4 concrete Caping slab on top of fence wall, to shade water away from wall | m3 | 1 |  | 0
F | supply and paint ring beam face capping slab | m2 | 4 |  | 0
| TOTAL FENCE |  |  |  | 0
11 | STREET SOLAR LIGHTINGS POLES
A | Supply and install street photocell Solar lighting as per drawings, solar street lighting poles with 65N Voltmax solar batteries. Fixed as per drawings from dormitory to class nearby classroom. (Note: 5 pcs are optional) | Nos | 20 |  | 0
| TOTAL STREET SOLAR LIGHTINGS |  |  |  | 0
12 | LANDSCAPING AND RESTORING VEGITATIONS
A | Supply and build stone masonry drainage dith 250mm thick (1:4) | m3 | 22.5 |  | 0
B | Supply and fix conrete slabs for covering a ditch, mix 1:2:4 with 6mm BRC | M3 | 4.05 |  | 0
C | Planting palm trees both sides along the unpaved walkway from the dormitory to nearby class | Nos | 100 |  | 0
D | Building stone masonry decorative seating benches around trees inside open sky area and out side building ( size is 1800mm dia by 300mm wide by 500 high and 400mm deep. | M3 | 7 |  | 0
E | Supply fertile soil (compost) and Plant glasses and flowers as directed by the consultant/client | m3 | 38 |  | 0
F | (optional) Pave all cut back slopes with grouted stones (stone lining) 250mm thick | m3 | 60 |  | 0
G | (optional) Kerbstones are built by using stones and make beautiful artistic views. | m | 200 |  | 0
| TOTAL LANDISCAPING |  |  |  | 0
GENERAL SUMMARY
| SUM FOR 84 GIRL'S DORMITORY |  |  |  | 0
| SUM TOILET AND LAUNDRY |  |  |  | 0
| TOTAL WATER TOWER |  |  |  | 0
| TOTAL INCINERATOR |  |  |  | 0
| TOTAL FENCE |  |  |  | 0
| TOTAL STREET SOLAR LIGHTINGS |  |  |  | 0
| TOTAL LANDISCAPING |  |  |  | 0
| SUM |  |  |  | 0
| CONTIGENCY 10% |  |  |  | 0
| VAT 18% |  |  |  | 0
| GRAND SUM 84 GIRL'S DORMITORY |  |  |  | 0

## 120 Girls dormitory - Ntamya sc
Bill of Quantities For the Construction of 120 girls dormitory in selected school at Kigoma MC&DC, Kasulu TC&DC and Kibondo DC Note: Unexcuted quantities will not be paid
S/No | Item | Unit | Qnt | Rate | Total
1 | PRELIMINARIES AND GENERAL COST
A | The Contractor shall be deemed to have visited the site and satisfied himself as to:- The nature of the site, The amount of bush, rubbish or debris to be cleared away before commencement, access to the site, availability of materials and the like. All the cost is for contractor |  |  | NA | NA
B | Allawance for material testing | Item | 1 |  | 0
C | Secure performance bond and insurance | Item | 1 |  | 0
D | Preparation of as built drawings | Item | 1 |  | 0
E | Mobilization and demobilization of tools, materials, manpower, and equipment. | Item | 1 |  | 0 |  | 0.6 | 0.60
F | Signboard and project registration | Item | 1 |  | 0 |  | 0.6 | 0.60 |  |  | Area for 84 | 23
G | Site Clearance: Removing bushes, shrubs, trees, etc. Clearing the site carefully without exceeding damaging tree near the constuction site; grubbing up roots bushes, shrub, undergrowth or the like; and removing all bushes surplus soil away keep clean for receiving materials | Item | 1 |  | 0 |  | 0.6 | 0.60 |  |  | defference | 10
H | Water for the works: The contractor shall allow for all necessary clean fresh water for the works, including that required by sub-contractors and for any temporary plumbing meters and storage facilities and pay all charges in connection therewith and clear away on completion and make good works disturbed. | Item | 1 |  | 0
I | Store and engineers office Supply and Construct temporary store for workers, engineer's office and materials to ensure proper storage of cement on raised floor with timbers and prevention of moisture is maintained . | Ls | 1 |  | 0 |  | 0.6 | 0.60 |  |  | factor the120 to get 50 by | 0.565217391
| SUB-TOTAL Emelement no 1: preliminaries |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
2 | SETTING OUT AND FOUNDATION | [7 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  |  |  | 0.6 | #VALUE!
[9 empty] | 0.6 | 0 |  |  | Area for 84 | 990
| Excavation | [7 empty] | 0.6 | 0 |  |  | Area for 120 | 1868.16
A | average 100 mm deep; to remove vegetable soil | m3 | 203 |  | 0 |  |  |  | 0.6 | 121.8 |  |  | difference | 878.16
B | Removing away from the site excavated material | m3 | 203 |  | 0 |  |  |  | 0.6 | 121.8 |  |  | 84 is less than 120 by | 0.88703
C | Excavate foundation trenches to commencing walling | m3 | 345 |  | 0 |  |  |  | 0.6 | 207
[9 empty] | 0.6 | 0
| Setting out and Foundation masonry | [7 empty] | 0.6 | 0
[9 empty] | 0.6 | 0
D | Dewatering Keeping excavations free from all water including spring and running water | Ls | 1 |  | 0 |  |  |  | 0.6 | 0.6
[9 empty] | 0.6 | 0
E | Stone masonry Foundation 600mm stone masonry wall: Mortar mixing ratio is 1:3 use 42.5N/mm2 cement strength Use big stones at least 40cm, hard, roughed surface texture, non round stones. Put big regular stone at conners. All stones are laid flat, all courses must alternate (zig zag) to prevent straight joint. Chop out rust layer around stone and clean with brush and water. Sett all dimensions as per drawing. Apply mortar to all joints close gaps with small stones. (Includes stairs and ramps) | m3 | 421 |  | 0 |  |  |  | 0.6 | 252.6
F | Backfilling Fill excavated soil from foundation treches ,compact in layers of 0.15cm and consolidate around foundation to achieve 98% maximum dry density (M.D.D) | m3 | 380 |  | 0 |  |  |  | 0.6 | 228
G | Hardcore 200 mm thick bed; levelled; compacted and blinded to receive polythene membrane; membrane; measured separately | m2 | 572 |  | 0 |  |  |  | 0.6 | 343.2
H | DPM Supply and lay 1000 gauge polythene Damp Proofing Membrane (with 150mm laps) over the sand blended into hardcores | M2 | 572 |  | 0 |  |  |  | 0.6 | 343.2
I | Anti-Termite ApplyTermite Killer; solution at the rate of 7 litres per square metre to hardcore beds | M2 | 572 |  | 0 |  |  |  | 0.6 | 343.2
J | Oversite conrete slab (1:3:6) Supply and pour plain concrete for oversite slab batched by volume a mixing ratio of 1:3:6 | m2 | 84 |  | 0 |  |  |  | 0.6 | 50.4
[9 empty] | 0.6 | 0
| RAMPS and STEPS (total of 7 ramps) | [7 empty] | 0.6 | 0
K | Foundation: Construct a 300mm thick stone masonry wall | m3 | 61 |  | 0 |  |  |  | 0.6 | 36.6
L | 400 mm thick hard core | m2 | 35 |  | 0 |  |  |  | 0.6 | 21
M | 100 mm thick, Plain concrete slab grade 15 | m2 | 35 |  | 0 |  |  |  | 0.6 | 21
[9 empty] | 0.6 | 0
| SUB-TOTAL ELEMEMNT No 2 - SUBSTRUCTURE |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
3 | ELEMENT No2: SUPERSTRUCTURE WALLS | [7 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  |  |  | 0.6 | #VALUE!
A | DPC 350mm wide horizontal bituminous hessian base damp proof course laid on oversite concrete with 150mm laps beds ready to receive ISSB walls. | m | 357 |  | 0 |  |  |  | 0.6 | 214.2
[9 empty] | 0.6 | 0
| EXTERNAL AND INTERNAL WALLING | [7 empty] | 0.6 | 0
B | Solid 230mm Thick hydraform walling external and internal walls, cost to include extraction and preparation of soil, block fabrication, curing and installation (with the strength of 3-5 MPa) | M2 | 1260 |  | 0 |  |  |  | 0.6 | 756
C | 750 mm high Perforated bricks wall, 230mm Thick hydraform external walling. Cost to include extraction and preparation of soil, block fabrication, curing and installation (with the strength of 3-5 MPa) | M2 | 145 |  | 0 |  |  |  | 0.6 | 87
CONCRETE WORK:
Reinforced insitu concrete grade ‘15’ including vibrating around reinforcements.
D | Horizontal beams ring beams | M3 | 28 |  | 0
REINFORCEMENTS
| High tensile steel bar reinforcement to BS 4449:1997, including cutting to length, bending, hoisting and fixing and all necessary tying wires and spacing blocks | [7 empty] | 0.6 | 0
[9 empty] | 0.6 | 0
E | 12mm diameter | Kgs | 3247 |  | 0
F | 8mm diameter | Kgs | 928 |  | 0
| FORMWORK TO INSITU CONCRETE | [7 empty] | 0.6 | #REF!
[9 empty] | 0.6 | #REF!
G | Supply and install formwork, including all necessary tools and materials for preparation and installation, as well as removal of the formwork once completed. | M2 | 235 |  | 0 |  |  |  | 0.6 | #REF!
H | Supply and cast 75mm diameter black pipe poles to suport roof at veranda | Nos | 15 |  | 0
[9 empty] | 0.6 | 0
| TOTAL ELEMENT NO 3: SUPERSTRUCTURE - Walls and Frames |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
4 | Roofing and water havesting | [7 empty] | 0.6 | 0
| Roof structure | [7 empty] | 0.6 | 0
A | Truss Fabrication and Installation • Materials: Supply well-seasoned and treated timber. Timber sections to be used: § Rafters: 50x150 mm. - eucaliptus § Tie beams: 50x150 mm. eucaliptus § Wall plates and struts: 50x100 mm. eucaliptus § Purlins: 50x70 mm. - Pine soft wood timber • Fabrication: Fabricate the trusses as per the provided drawings. Ensure the trusses are fabricated with a rafter slope of 8 degrees. • Installation: Install the fabricated trusses on the ring beam with a spacing of 1.4 meters center-to-center (c/c). Anchor the trusses to the ring beam using core M6 steel bars casted in the ring beam. Use two bolts (12mm diameter) with nuts and 2inches diameter washers to secure the joints of rafters and tie beams. • Overhangs: o The external overhang is to be 1.5 meters long. o The internal overhang at the hallway is to be 0.8 meters long. • Additional Provisions: o All tools, nails, and materials necessary for the truss fabrication and installation are to be included Note: Trusses spanning the entire width of the building will be counted. The shorter trusses will be estimated to form a complete large truss for payment calculation. | Nos | 169 |  | 0 | treated Eucalyptus timber Rafters - 50x150mm, sloped at an angle of 4 degree |  |  | 0.6 | 101.4
B | Supply and fix 28 gaurge IT5 colorless but not transparant covering sheets, fixed on streated pine timber purlins with rubbered roofing nails of 3.5 inches length | m2 | 1168 |  | 0 | IT5 colorless but not trasperant covering sheets, fixed on streated pine timber purlins with roofing nails of 3.5 inches length |  |  | 0.6 | 700.8
C | Supply and fix a Fascia board: use well seasoned and treated pine timber - 25x200mm. fix brackets with screw of a lenght of 1.5 inches , fixed at 600mm c/c | m | 298 |  | 0 | Fascia board: treated pine timber - 25x200mm. Weld brackets at 600mm c/c |  |  | 0.6 | 178.8
D | Supply and fix Valley cap, 450mm girth | LM | 135 |  | 0
E | Ceiling Supply and install 50x50 mm treated pine timber brandering, plain gypsum conices, and fix 9mm thick gypsum board as per Thailand or the like. | M2 | 662 |  | 0
F | Optional quantity for modifications or expansion of the roof in public space: Supply and install a complete steel roof truss structure plus IT5 roof covering. | m2 | 49 |  | 0 |  |  |  | 0.6 | 29.4
G | supply a micro coffee mesh wire and fix it behind the perforated fill masonry wall on top of ring beam to prevent dust from entering the top of the ceiling. Further instruction to e given by engineer on site. | m2 | 106 |  | 0 |  |  |  | 0.6 | 63.6
[9 empty] | 0.6 | 0
| Water harvesting systeam | [7 empty] | 0.6 | 0
H | Gutters Supply and fix class B PVC gutter 150mm diameter by 75mm deep. Including 75mm downpipes, 500mm c/c brackets, plus all required fittings and glues. | m | 177.3 |  | 0 |  |  |  | 0.6 | 106.38
I | Storrage poly tanks Supply and install 4 sim tanks of 5,000 litres each and build a ground base of stone masonry post with atwo crossing walls at the middle 600mm high from the ground, 700mm deep, 500mm width, 180mm diameter, 150mm thick concrete grade 20 with 6mm BRC. | Nos | 4 |  | 0 |  |  |  | 0.6 | 2.4
D | Supply and cast 75mm diameter black pipe poles to suport roof at veranda. Use conrete grade 20 to cast it. | Nos | 25 |  | 0
[9 empty] | 0.6 | 0
| TOTAL ELEMENT No 4: ROOFING AND RAIN WATER HARVESTING |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
5 | FINISHING | [7 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  |  |  | 0.6 | #VALUE!
| Plastering | [7 empty] | 0.6 | 0
A | External wall: foundation Pointing a stone masonry foundation wall 1:3 cement sand and apply three coats of black and white paint around the pointing strips only not to stones surfaces | m2 | 153 |  | 0 |  |  |  | 0.6 | 91.8
B | External wall: superstructure Plaster 1:3 cement sand, 25mm thick 0.5m high from DPC level | m2 | 180 |  | 0 |  |  |  | 0.6 | 108
C | Externally: apply a 25mm thick Plaster 1:4 cement sand to all beams, and corners of the walls and around windows a strip of 75mm wide | m2 | 139 |  | 0 |  |  |  | 0.6 | 83.4
[5 empty] | 0 |  |  |  | 0.6 | 0
| Internal walls finishing (1:4) |  |  |  | 0 |  |  |  | 0.6 | 0
D | Plastering 25mm thick to obtain a smooth finish then skim with lime. | m2 | 1308 |  | 0 |  |  |  | 0.6 | 784.8
[5 empty] | 0 |  |  |  | 0.6 | 0
| Floor finishing |  |  |  | 0 |  |  |  | 0.6 | 0
E | Terrazzo floor finish including 150mm high skirtings | m2 | 662 |  | 0 |  |  |  | 0.6 | 397.2
[5 empty] | 0 |  |  |  | 0.6 | 0
| Painting and decoration works |  |  |  | 0 |  |  |  | 0.6 | 0
| Externally |  |  |  | 0 |  |  |  | 0.6 | 0
F | Clean and apply three coat of seed oil or apply a varnish to all ISSB external walls | m2 | 728 |  | 0 |  |  |  | 0.6 | 436.8
G | Supply and Skimming to obtain a smooth finish, clean, prime and Apply water-based weather guard paint to all plastered columns and beams and windows | m2 | 139 |  | 0 |  |  |  | 0.6 | 83.4
[5 empty] | 0 |  |  |  | 0.6 | 0
| Internally: supply,skim,clean and apply |  |  |  | 0 |  |  |  | 0.6 | 0
H | Emulsion Painting to internal wall surfaces | m2 | 1308 |  | 0 |  |  |  | 0.6 | 784.8
I | Emulsion Painting to Celling (rooms and verandah | m2 | 570 |  | 0 |  |  |  | 0.6 | 342
J | Oil-based painting fascia board, metal doors, grills and windows | m2 | 95 |  | 0 |  |  |  | 0.6 | 57
[9 empty] | 0.6 | 0
| SUB-TOTAL ELEMENT No 5- FINISHING |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
6 | ELECTRICAL INSTALLATION | [7 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  |  |  | 0.6 | #VALUE!
A | Electrical Installation (ABB or Tronic standard): Electricity wiring and connection to powerline without buying/istallation of an electrical poles: Installing wiring and electrical equipment as per drawing Energy saver LED BULB Complete with straight Complete, Use single core wires pure copper, double eath rod approved pure copper 16sqmm each. NB: Cables for 1.5sqmm 2.5sqmm, 4sqmm, 6sqmm, 10sqmm should be EURO or other equal approved | Sum | 1 |  | 0 |  |  |  | 0.6 | #REF!
[9 empty] | 0.6 | 0
| TOTAL ELEMENT No 6: ELECTRICITY INSTALLATION |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
7 | DOORS FRAME AND SHUTTER | [7 empty] | 0.6 | 0
S/No | Item | Unit | Qnt | Rate | Total |  |  |  | 0.6 | #VALUE!
A | Doors Shutter Prime quality hardwood paneled doors mninga or other equal and approved hardwood 45mm Thick panelled single door Mahogany timber finish, comprising of 45 x 150mm top and middle rails, 45 x 150mm stiles and 45 x 200 bottom rail, panels filled in with and including 35mm thick moulded boarding tongued and grooved all round rails Including Supply and fix the following "UNION" make or other equal and approved iron-mongery To softwood, hardwood or the like; fixing with screws ;- 3-Lever Mortise lock with furniture, Toiles and Bathroom lock with indicating bolt, 100mm Brass butt hinges | [7 empty] | 0.6 | 0
B | Ditto 900 x 2100mm high. | No | 32 |  | 0 |  |  |  | 0.6 | 19.2
| Supply and install Metal gates/doors | [7 empty] | 0.6 | 0
C | 1500x2100mm high ( for main exits gates) | Nos | 3 |  | 0 |  |  |  | 0.6 | 1.8
| Supply and fix Door frames: Hardwood mininga or other equal and approved hardwood. Provide 16mm diameter burglar bars 150mm c/c , fix perforated 5mm thick clear sheet glass glazed to hardwood frame with glazing beads and fix a clear mosiquito wire net to prevent dust ant insects. | [7 empty] | 0.6 | 0
D | Ditto 950x2800mm high | Nos | 32 |  | 0 |  |  |  | 0.6 | 19.2
[9 empty] | 0.6 | 0
[9 empty] | 0.6 | 0
| TOTAL ELEMENT NO 7: DOORS |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
8 | Windows | [7 empty] | 0.6 | 0
| Supply and fix metal windows with openable grills fix with tinted glass glazing, perforated ventilation with clear glass glazing, and two sliding panels fixed with mosquitor wire net. Use 25x50mm hallow section steel stiles, 38x38mm HS grills, 25x25mm angle line steel for glazing, Inclding all iron mongeries | [7 empty] | 0.6 | 0
A | Ditto 1500x2000mm High | Nos | 33 |  | 0 |  |  |  | 0.6 | 19.8
[9 empty] | 0.6 | 0
| TOTAL ELEMENT NO 8: WINDOWS |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
9 | EQUIPMENT | [7 empty] | 0.6 | 0
| FIRE FIGHTING INSTALLATION | [7 empty] | 0.6 | 0
A | Supply and install 9KG, dry powder 'NAFFCO' or 'ANGUS' any other equal and approved fire extinguishers | Nos | 4 |  | 0 |  |  |  | 0.6 | 2.4
B | Stand alone smoke detector | Nos | 10 |  | 0 |  |  |  | 0.6 | 6
[9 empty] | 0.6 | 0
9 | TROTAL ELEMENT NO 9: FIRE FIGHITING EQUIPLENTS |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
SUB SUMMARY DORMITORY ROOMS | [8 empty] | 0.6 | 0
1 | SUB-TOTAL Emelement no 1: preliminaries |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
2 | SUB-TOTAL ELEMEMNT No 2 - SUBSTRUCTURE |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
3 | TOTAL ELEMENT NO 3: SUPERSTRUCTURE - Walls and Frames |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
4 | TOTAL ELEMENT No 4: ROOFING AND RAIN WATER HARVESTING |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
5 | SUB-TOTAL ELEMENT No 5- FINISHING |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
6 | ELECTRICAL INSTALLATION |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
7 | TOTAL ELEMENT NO 7: DOORS |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
8 | TOTAL ELEMENT NO 8: WINDOWS |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
9 | TROTAL ELEMENT NO 9: FIRE FIGHITING EQUIPLENTS |  |  |  | 0 |  |  |  | 0.6 | 0
[9 empty] | 0.6 | 0
| SUM FOR 84 GIRL'S DORMITORY |  |  |  | 0 |  |  |  | 0.6 | 0
TOILETS and LAUNDRY
1 | Foundation and walling
A | Site cleance and excavation of foundations | m3 | 58 |  | 0
B | Foundation masonry stone walls 1:3 | m3 | 73 |  | 0
C | Plain Oversite conrete 1:3:6, DPM first | m2 | 8 |  | 0
D | Supply and cast 75mm diameter black pipe poles to suport roof at veranda. Use conrete grade 20 to cast it. | Nos | 2 |  | 0
E | Walling using ISSB blocks,on DPC | m2 | 226 |  | 0
CONCRETE WORK:
Reinforced insitu concrete grade ‘15’ including vibrating around reinforcements.
F | Concrete | M3 | 3 |  | 0
| High tensile steel bar reinforcement to BS 4449:1997, including cutting to length, bending, hoisting and fixing and all necessary tying wires and spacing blocks | [5 empty] | 0.6 | 0
G | 12mm diameter | Kgs | 200 |  | 0
H | 8mm diameter including binding wire | Kgs | 125 |  | 0
| M6 bars for truss arnchoring, to be casted with ring beams and potrudes out of conrete by 400mm length | Kgs | 52 |  | 0
| FORMWORK TO INSITU CONCRETE | [5 empty] | 0.6 | 0
| Sides,Vertical or Battering | [5 empty] | 0.6 | 0
I | Supply, fix formworks and formworks removal, including all tools and materials needed for preparation and installation | M2 | 45 |  | 0 |  | 0.6 | #REF!
| TOTAL FOUNDATION AND WALLING |  |  |  | 0
2 | Roof structure
A | Truss Fabrication and Installation • Materials: Supply well-seasoned and treated timber. Timber sections to be used:  Rafters: 50x150 mm. - eucaliptus  Tie beams: 50x150 mm. eucaliptus  Wall plates and struts: 50x100 mm. eucaliptus  Purlins: 50x70 mm. - Pine soft wood timber • Fabrication: Fabricate the trusses as per the provided drawings. Ensure the trusses are fabricated with a rafter slope of 8 degrees. • Installation: Install the fabricated trusses on the ring beam with a spacing of 1.4 meters center-to-center (c/c). Anchor the trusses to the ring beam using core M6 steel bars casted in the ring beam. Use two bolts (12mm diameter) with nuts and 2inches diameter washers to secure the joints of rafters and tie beams. • Overhangs: o The external overhang is to be 1.5 meters long. o The internal overhang at the hallway is to be 0.8 meters long. • Additional Provisions: o All tools, nails, and materials necessary for the truss fabrication and installation are to be included | Nos | 12 |  | 0 |  | 0.6 | 7.2
B | Supply and fix 28 gaurge IT5 colorless but not transparant covering sheets, fixed on streated pine timber purlins with rubbered roofing nails of 3.5 inches length | m2 | 137 |  | 0
C | Supply and fix a Fascia board: use well seasoned and treated pine timber - 25x200mm. fix brackets with screw of a lenght of 1.5 inches , fixed at 600mm c/c | m | 44 |  | 0
0
| TOTAL ROOFING |  |  |  | 0
3 | RC Concrete dhobi sinks |  |  |  | 0
A | Construct a (1:2:4) 6mm BRC reinforced concrete wash basin with a 600mm x 400mm width by 350mm depth internal dimension, and provide a 50mm diameter water outlet hole provided with trap and screener, 100mm concrete partition wall between one wash basin to another same for slab. Top-level of wash basin from floor is 750mm, it will be casted on top of brick wall, includes formworks, bottle trap, drainers and necessary accessories; ( it will be used as hand wash basin as well) . Apply Terrazzo finishing to all dhobi sinks | m3 | 4.5 |  | 0
| TOTAL DHOBI SINKS |  |  |  | 0
4 | DOORS
Doors Shutter Prime quality hardwood paneled doors mninga or other equal and approved hardwood 45mm Thick panelled single door Mahogany timber finish, comprising of 45 x 150mm top and middle rails, 45 x 150mm stiles and 45 x 200 bottom rail, panels filled in with and including 35mm thick moulded boarding tongued and grooved all round rails Including Supply and fix the following "UNION" make or other equal and approved iron-mongery To softwood, hardwood or the like; fixing with screws ;- 3-Lever Mortise lock with furniture, Toiles and Bathroom lock with indicating bolt, 100mm Brass butt hinges
A | Ditto 800 x 2000mm high. ( toilets and changing room) | No | 16 |  | 0
B | Ditto 1000 x 2000mm high, provide with 900mm door handle , double swing hinges to open inward and outward swing. PWD | No | 1 |  | 0
C | Metal door 900x2000mm high ( at incinerator area) | Nos | 1 |  | 0
Supply and fix Door frames: Hardwood mininga or other equal and approved hardwood. Provide 16mm diameter burglar bars 150mm c/c , fix perforated 5mm thick clear sheet glass glazed to hardwood frame with glazing beads and fix a clear mosiquito wire net to prevent dust ant insects.
D | Ditto 850x2800mm high (Changing room and insinerator) | Nos | 2 |  | 0
E | 850x2000mm , high no vents, no glass, no buglar bars ( for Toilets) | Nos | 14 |  | 0
F | 1050x2000mm high no vents, no glass, no buglar bars ( for Toilets-PWD) | Nos | 1 |  | 0
| TOTAL DOORS |  |  |  | 0
5 | Windows
A | Ditto1000x600 High ( Toilet) | Nos | 7 |  | 0
| TOTAL WINDOW |  |  |  | 0
6 | Finishing
A | Plastering 25mm thick 1:3 cement sand to foundation wall and to internal walls | m2 | 168 |  | 0
B | water proof plaster in inernal toilet walls and terrazzo to laundry and above wash basin | m2 | 99 |  | 0
C | Terrazzo floor finish including 150mm high skirtings | m2 | 130 |  | 0
D | Vanish exernal ISSB wall | m2 | 115 |  | 0
E | Painting three coats of bituminous paint to foundation walls, Paint to internal walls and to beams, painting red oxide to trusses and fascia board | m2 | 45 |  | 0
| TOTAL FINISHING |  |  |  | 0
7 | Plumbing and Sanitary Installation
Supply and fix ;
A | Wash hand basins; white vitreous China; 32mm chromium plated chain waste 32mm plastic bottle trap concealed bracket with fixing clamps pair 12mm pillar taps 420 x 510mm; requiring plugging. fixing with brass screws to backgrounds ( install at changing/women's room and at disabled toilet room) | Nos | 2 |  | 0
B | Squatting -White vitreous asian type W.C suite comprising 9 litres capacity cistern with cover, 12mm BSS high pressure ball valve, plastic syphon fitting, side supply and overflow set | Nos | 8 |  | 0
C | Complete disabled toilets, grab rails, mixer, floor drainer and all nesessary accessories | Nos | 1 |  | 0
D | 80mm Diameter high quality plastic floor drain trap built in concrete bed | Nos | 8 |  | 0
E | 6mm silver mirror, lead backed, size 450 x600mm with arise edges fixed to wall with mirror screws | Nos | 5 |  | 0
F | 20mmØ Chromium plated towel single rail, 600mm long | Nos | 7 |  | 0
G | 100mm long soap holder (PVC), plugged and screwed to brick wall | Nos | 6 |  | 0
H | Shurtuff (Douche spray) 13mm diameter X 1000mm long flexible hose metal braided hose | Nos | 11 |  | 0
I
J | Pipes work in building
K | A: Supply pipe PN 16
L | 25mmØ communication pipe HDPE to trench | m | 45 |  | 0
M | Ditto; tee | Nos | 16 |  | 0
N | Ditto; elbow | Nos | 25 |  | 0
O | Ditto; male connector | Nos | 16 |  | 0
P | 32mmØ pipe to trench | Nos | 32 |  | 0
Q | Ditto; elbow | Nos | 6 |  | 0
R | Ditto; nipple MM | Nos | 25 |  | 0
S | Ditto; nipple FF | Nos | 25 |  | 0
T | Ditto; union | Nos | 18 |  | 0
U | Ditto; reducing connector 32Ø × 25Ø | Nos | 27 |  | 0
V | Ditto; reducing connector 25Ø × 19Ø | Nos | 27 |  | 0
W | Ditto; nipple MM | Nos | 27 |  | 0
X | Ditto; reducing connector 19Ø × 13Ø | Nos | 27 |  | 0
Y | 13mm diameter pipe in blockwall chase BS 1010 or 1212 | m | 45 |  | 0
Z | Ditto; elbow | Nos | 55 |  | 0
AA | Ditto; tee. | Nos | 28 |  | 0
AB | Ditto: nipple MM | Nos | 28 |  | 0
AC | Ditto: nipple FF | Nos | 28 |  | 0
AD | Ditto: union | Nos | 28 |  | 0
B: WASTE AND VENT PIPES
UPVC pipes: class 'C'
AE | 38mmØ; chase in block in concrete slab. | m | 28 |  | 0
AF | Ditto: Equal tee | Nos | 14 |  | 0
AG | Ditto; plain elbow | Nos | 8 |  | 0
AH | Ditto; plugged elbow | Nos | 8 |  | 0
AI | C: SOIL AND PIPES
AJ | UPVC pipes and fittings: Class 'C'
AK | 100mmØ pipe fixed to walls | m | 12 |  | 0
AL | Ditto; laid in trenches. | m | 45 |  | 0
AM | Ditto; plugged bend 90˚. | Nos | 14 |  | 0
AN | Ditto; plain bend 90˚. | Nos | 14 |  | 0
D: Ancillaries:
Draw off taps; stop valves; copper alloy to BS 5154 or BS 1010
AO | 13mmØ stop valve | Nos | 30 |  | 0
AP | 13mm Ø bib taps Chrome plated | Nos | 30 |  | 0
AQ | 13mm angle valves | Nos | 11 |  | 0
AR | Provision for wastebin for waste collection in the MHM room | Nos | 3 |  | 0
FOUL WATER DRAINAGE
MANHOLE AND GULLY TRAP
AS | Construct a masonry manhole size 600 x x600mm average depth 600mm with fired bricks, mortar ratio 1:3 | Nos | 9 |  | 0
AT | Construct a standard gully trap chambers with internal dimensions of 300x300mm by 300mm deep using burnt bricks | Nos | 13 |  | 0
0
0
| Soak way pit |  |  |  | 0
AU | Construct complete soak away pit, size 3m diam with 3.5m depth, including excavation, perforated brick wall, pipe 4" connection, vent pipe 4",Y12 150 C/C top and bottom face reinforced concrete slab 150mm thick, formwork, precast concrete cover 450 x 450mm | LS | 1 |  | 0
0
Septic Tank
AV | Allow for construction of faul water septic tank of internal dimension 5000Lx2000Wx3000D mm, of capacity 17,280Litres complete , Y12 150 c/c bottom face reinforced concrete grade 20 , formwork and other associated accessories | LS | 1 |  | 0
| TOTAL PLUMBING AND SANITARY ISTALLATION |  |  |  | 0
SUB SUMMARY - TOILET
| Foundation and walling |  |  |  | 0
| Roof structure |  |  |  | 0
| Finishing |  |  |  | 0
| Plumbing and Sanitary Installation |  |  |  | 0
| SUM TOILET AND LAUNDRY |  |  |  | 0
8 | WATER TOWER
A | Site cleance and excavation of foundations | m3 | 13 |  | 0
B | Masonry foundation wall | m2 | 46 |  | 0
C | 300mm thick Walling with fired bricks | m2 | 140 |  | 0
D | Supply and cast concrete grade 15 for oversite concrete | m2 | 28 |  | 0
E | RC concrete beams 4Y12 main bars, Y8-200c/c stirups, formworks | m3 | 1 |  | 0
F | RC concrete beams 4Y16 main bars, Y8-200c/c stirups, formworks. | M3 | 0.44 |  | 0
G | RC conrete roof slab mix ratio 1:2:4, Y12-175 c/c- use cement 42.5Nmm2 , formworks | m3 | 1.29 |  | 0
H | Construct four (4) reinforced concrete columns, column footings 4Y12 main bars, Y8-200c/c stirups, formworks. | m3 | 3 |  | 0
I | Plastering and skiming with lime ( optional) | m2 | 35 |  | 0
J | Painting ( optional) | m2 | 35 |  | 0
K | Supply and install 1000x2500 metal door with all accessories including padlocks for the store. | Nos | 1 |  | 0
L | Supply and install a sim tanks of 10,000 litres | Nos | 1 |  | 0
M | Supply and install a sim tanks of 5,000 litres | Nos | 1 |  | 0
| TOTAL WATER TOWER |  |  |  | 0
9 | INCINERATOR
A | Excavations | m3 | 2.5 |  | 0
B | Masonry stone foundation wall , motar 1:3 cement sand | m3 | 2.03 |  | 0
C | Fired brick 230mm walls 980x780mm internally by | m2 | 9.152 |  | 0
D | concrete grade 20 (1:2:4) reinforced with 6mm BRC | m3 | 0.254 |  | 0
E | Reinforcement Y16 for burning platform | Kgs | 36.4 |  | 0
F | 150mm thick fired brick walls for 4.6m Chimney length jointed with cement mortar 1:3 | m2 | 4.214 |  | 0
Finishing
G | Pointing works and Panting works to ring beam surface color to be directed by the clien | m2 | 19.5 |  | 0
H | W3 - 400x400 metal window for incinarator | Nos | 1 |  | 0
I | W4 - 300X300 incinerator | Nos | 1 |  | 0
J | W5 - 150x150 Incinerator | Nos | 1 |  | 0
| TOTAL INCINERATOR |  |  |  | 0
10 | FENCE
A | Excavations of foundation | m3 | 4 |  | 0
B | Stone masonry foundation wall 500mm high from ground level , mortar 1:3 cement sand | m3 | 8 |  | 0
C | 230mm thick ISSB walling on DPC | m2 | 27 |  | 0
D | RC concrete beam at 1.8m from DPC LEVEL , c.rario 1:2:4 with 4Y12 and Y8-200C/C, including formworks. | m3 | 1 |  | 0
E | 6mm BRC, 1:2:4 concrete Caping slab on top of the fence wall, to shade water away from wall | m3 | 1 |  | 0
F | supply and paint the ring beam face of capping slab | m2 | 4 |  | 0
| TOTAL FENCE |  |  |  | 0
11 | STREET SOLAR LIGHTINGS POLES
A | Supply and install street photocell Solar lighting as per drawings, solar street lighting poles with 65N Voltmax solar batteries. Fixed as per drawings from dormitory to class nearby classroom. (Note: 5 pcs are optional) | Nos | 20 |  | 0
| TOTAL STREET SOLAR LIGHTINGS |  |  |  | 0
12 | LAND SCAPING AND RESTORING VEGITATIONS
A | Supply and build stone masonry drainage dith 250mm thick (1:4) | m3 | 22.5 |  | 0
B | Supply and fix conrete slabs for covering a ditch, mix 1:2:4 with 6mm BRC | M3 | 4.05 |  | 0
C | Planting palm trees both sides along the unpaved walkway from the dormitory to nearby class | Nos | 100 |  | 0
D | Building stone masonry decorative seating benches around trees inside open sky area and out side building ( size is 1800mm dia by 300mm wide by 500 high and 400mm deep. | M3 | 7 |  | 0
E | Supply fertile soil (compost) and Plant glasses and flowers as directed by the consultant/client | m3 | 38 |  | 0
F | (optional) Pave all cut back slopes with grouted stones (stone lining) 250mm thick | m3 | 60 |  | 0
G | (optional) Kerbstones are built by using stones and make beautiful artistic views. | m | 200 |  | 0
| TOTAL LANDISCAPING |  |  |  | 0
GENERAL SUMMARY
| SUM FOR 84 GIRL'S DORMITORY |  |  |  | 0
| SUM TOILET AND LAUNDRY |  |  |  | 0
| TOTAL WATER TOWER |  |  |  | 0
| TOTAL INCINERATOR |  |  |  | 0
| TOTAL FENCE |  |  |  | 0
| TOTAL STREET SOLAR LIGHTINGS |  |  |  | 0
| TOTAL LANDISCAPING |  |  |  | 0
| SUM |  |  |  | 0
| CONTIGENCY 10% |  |  |  | 0
| VAT 18% |  |  |  | 0
| GRAND SUM 84 GIRL'S DORMITORY |  |  |  | 0

## WASH FACILITIES- for 7 schools
Bill of Quantities For the Construction of WASH facilities in selected 20 school at Kigoma MC&DC, Kasulu TC&DC and Kibondo DC Note: Unexcuted quantities will not be paid
TOILETS
1 | Foundation and walling
A | Site cleance and excavation of foundations | m3 | 41 | 0
B | Foundation masonry stone walls 1:3 | m3 | 43 | 0
C | Plain Oversite conrete 1:3:6, DPM first | m2 | 72 | 0
D | Supply and cast 75mm diameter black pipe poles to suport roof at veranda. Use conrete grade 20 to cast it. | Nos | 2 | 0
E | Walling using ISSB blocks,on DPC | m2 | 157.82 | 0
CONCRETE WORK:
Reinforced insitu concrete grade ‘15’ including vibrating around reinforcements.
F | Concrete | M3 | 2.3 | 0
| High tensile steel bar reinforcement to BS 4449:1997, including cutting to length, bending, hoisting and fixing and all necessary tying wires and spacing blocks |  |  |  | 0.6 | 0
G | 12mm diameter | Kgs | 150 | 0
H | 8mm diameter including binding wire | Kgs | 82 | 0
| M6 bars for truss arnchoring, to be casted with ring beams and potrudes out of conrete by 400mm length | Kgs | 30 | 0
| FORMWORK TO INSITU CONCRETE |  |  |  | 0.6 | 0
| Sides,Vertical or Battering |  |  |  | 0.6 | 0
I | Supply, fix formworks and formworks removal, including all tools and materials needed for preparation and installation | M2 | 25 | 0 | 0.6 | #REF!
| TOTAL FOUNDATION AND WALLING |  |  | 0
2 | Roof structure
A | Truss Fabrication and Installation • Materials: Supply well-seasoned and treated timber. Timber sections to be used:  Rafters: 50x150 mm. - eucaliptus  Tie beams: 50x150 mm. eucaliptus  Wall plates and struts: 50x100 mm. eucaliptus  Purlins: 50x70 mm. - Pine soft wood timber • Fabrication: Fabricate the trusses as per the provided drawings. Ensure the trusses are fabricated with a rafter slope of 8 degrees. • Installation: Install the fabricated trusses on the ring beam with a spacing of 1.4 meters center-to-center (c/c). Anchor the trusses to the ring beam using core M6 steel bars casted in the ring beam. Use two bolts (12mm diameter) with nuts and 2inches diameter washers to secure the joints of rafters and tie beams. • Overhangs: o The external overhang is to be 1.5 meters long. o The internal overhang at the hallway is to be 0.8 meters long. • Additional Provisions: o All tools, nails, and materials necessary for the truss fabrication and installation are to be included | Nos | 9 | 0 | 0.6 | 5.4
B | Purlins- treated Pine timber 50x75mm | m | 65.1 | 0
C | IT5 colorless but not trasperant covering sheets, fixed on streated pine timber purlins with roofing nails of 3.5 inches length | m2 | 137 | 0
D | Fascia board: treated pine timber - 25x200mm. fix brackets with srews 1.5cm long, brackets to be spaced at 600mm c/c | m | 30.1 | 0
0
| TOTAL ROOFING |  |  | 0
3 | RC Concrete dhobi sinks |  |  | 0
A | Construct a (1:2:4) 6mm BRC reinforced concrete wash basin with a 600mm x 400mm width by 350mm depth internal dimension, and provide a 50mm diameter water outlet hole provided with trap and screener, 100mm concrete partition wall between one wash basin to another same for slab. Top-level of wash basin from floor is 750mm, it will be casted on top of brick wall, includes formworks, bottle trap, drainers and necessary accessories; ( it will be used as hand wash basin as well) | m3 | 3.2 | 0
| Total Dhobi Sinks |  |  | 0
4 | DOORS
Doors Shutter Prime quality hardwood paneled doors mninga or other equal and approved hardwood 45mm Thick panelled single door Mahogany timber finish, comprising of 45 x 150mm top and middle rails, 45 x 150mm stiles and 45 x 200 bottom rail, panels filled in with and including 35mm thick moulded boarding tongued and grooved all round rails Including Supply and fix the following "UNION" make or other equal and approved iron-mongery To softwood, hardwood or the like; fixing with screws ;- 3-Lever Mortise lock with furniture, Toiles and Bathroom lock with indicating bolt, 100mm Brass butt hinges
A | Ditto 800 x 2000mm high. ( toilets and changing room) | No | 11 | 0
B | Ditto 1000 x 2000mm high, provide with 900mm door handle , double swing hinges to open inward and outward swing. PWD | No | 1 | 0
C | Metal door 900x2000mm high ( at incinerator area) | Nos | 1 | 0
Supply and fix Door frames: Hardwood mininga or other equal and approved hardwood. Provide 16mm diameter burglar bars 150mm c/c , fix perforated 5mm thick clear sheet glass glazed to hardwood frame with glazing beads and fix a clear mosiquito wire net to prevent dust ant insects.
D | Ditto 850x2800mm high (Changing room and incinerator) | Nos | 2 | 0
E | 850x2000mm , high no vents, no glass, no buglar bars ( for Toilets) | Nos | 10 | 0
F | 1050x2000mm high no vents, no glass, no buglar bars ( for Toilets-PWD) | Nos | 1 | 0
| TOTAL DOORS |  |  | 0
5 | Windows
A | Ditto1000x600 High ( Toilet) | Nos | 10 | 0
| TOTAL WINDOW |  |  | 0
6 | Finishing
A | Plastering 25mm thick 1:3 cement sand to foundation wall and to internal walls | m2 | 117.18 | 0
B | water proof plaster in inernal toilet walls and terrazzo to laundry and above wash basin | m2 | 69.16 | 0
C | Terrazzo floor incl 150mm high skirtings | m2 | 91 | 0
D | Vanish exernal ISSB wall | m2 | 80.29 | 0
E | Painting three coats of bituminous paint to foundation walls, internal walls and to beams, painting red oxide to trusses and fascia board | m2 | 31.08 | 0
| TOTAL FINISHING |  |  | 0
7 | Plumbing and Sanitary Installation
Supply and install and test ;
A | Wash hand basins; white vitreous China; 32mm chromium plated chain waste 32mm plastic bottle trap concealed bracket with fixing clamps pair 12mm pillar taps 420 x 510mm; requiring plugging. fixing with brass screws to backgrounds ( install at changing/women's room and at disabled toilet room) | Nos | 2 | 0
B | Squatting -White vitreous asian type W.C suite comprising 9 litres capacity cistern with cover, 12mm BSS high pressure ball valve, plastic syphon fitting, side supply and overflow set | Nos | 6 | 0
C | Complete disabled toilets, grab rails, mixer, floor drainer and all nesessary accessories | Nos | 1 | 0
D | 80mm Diameter high quality plastic floor drain trap built in concrete bed | Nos | 6 | 0
E | 6mm silver mirror, lead backed, size 450 x600mm with arise edges fixed to wall with mirror screws | Nos | 4 | 0
F | 20mmØ Chromium plated towel single rail, 600mm long | Nos | 5 | 0
I | 100mm long soap holder (PVC), plugged and screwed to brick wall | Nos | 5 | 0
J | Shurtuff (Douche spray) 13mm diameter X 1000mm long flexible hose metal braided hose | Nos | 8 | 0
Pipes work in building
A: Supply pipe PN 16
K | 25mmØ communication pipe HDPE to trench | m | 31.5 | 0
L | Ditto; tee | Nos | 12 | 0
N | Ditto; elbow | Nos | 18 | 0
M | Ditto; male connector | Nos | 12 | 0
N | 32mmØ pipe to trench | Nos | 23 | 0
O | Ditto; elbow | Nos | 5 | 0
P | Ditto; nipple MM | Nos | 18 | 0
Q | Ditto; nipple FF | Nos | 18 | 0
R | Ditto; union | Nos | 13 | 0
S | Ditto; reducing connector 32Ø × 25Ø | Nos | 19 | 0
T | Ditto; reducing connector 25Ø × 19Ø | Nos | 19 | 0
U | Ditto; nipple MM | Nos | 19 | 0
V | Ditto; reducing connector 19Ø × 13Ø | Nos | 19 | 0
W | 13mm diameter pipe in blockwall chase BS 1010 or 1212 | m | 32 | 0
X | Ditto; elbow | Nos | 39 | 0
Y | Ditto; tee. | Nos | 20 | 0
Z | Ditto: nipple MM | Nos | 20 | 0
AC | Ditto: nipple FF | Nos | 20 | 0
AD | Ditto: union | Nos | 20 | 0
B: WASTE AND VENT PIPES
UPVC pipes: class 'C'
AE | 38mmØ; chase in block in concrete slab. | m | 20 | 0
AF | Ditto: Equal tee | Nos | 10 | 0
AG | Ditto; plain elbow | Nos | 6 | 0
AH | Ditto; plugged elbow |  | 6 | 0
AI | C: SOIL AND PIPES
AJ | UPVC pipes and fittings: Class 'C'
AK | 100mmØ pipe fixed to walls | m | 9 | 0
AL | Ditto; laid in trenches. | m | 32 | 0
AM | Ditto; plugged bend 90˚. | Nos | 10 | 0
AN | Ditto; plain bend 90˚. | Nos | 10 | 0
D: Ancillaries:
Draw off taps; stop valves; copper alloy to BS 5154 or BS 1010
AO | 13mmØ stop valve | Nos | 21 | 0
AP | 13mm Ø bib taps Chrome plated | Nos | 21 | 0
AQ | 13mm angle valves | Nos | 8 | 0
AR | Provision for wastebin for waste collection in the MHM room | Nos | 2 | 0
FOUL WATER DRAINAGE
MANHOLE AND GULLY TRAP
AS | Construct a masonry manhole size 600 x x600mm average depth 600mm with fired bricks, mortar ratio 1:3 | Nos | 7 | 0
AT | Construct a standard gully trap chambers with internal dimensions of 300x300mm by 300mm deep using burnt bricks | Nos | 10 | 0
0
0
| Soak way pit |  |  | 0
AU | Construct complete soak away pit, size 3m diam with 3.5m depth, including excavation, perforated brick wall, pipe 4" connection, vent pipe 4",Y12 150 C/C top and bottom face reinforced concrete slab 150mm thick, formwork, precast concrete cover 450 x 450mm | LS | 1 | 0
0
Septic Tank
AV | Allow for construction of faul water septic tank of internal dimension 5000Lx2000Wx3000D mm, of capacity 17,280Litres complete , Y12 150 c/c bottom face reinforced concrete grade 20 , formwork and other associated accessories | LS | 1 | 0
3 | RC Concrete dhobi sinks |  |  | 0 |  |  | 0.7 | 0
A | Construct a (1:2:4) 6mm BRC reinforced concrete wash basin with a 600mm x 400mm width by 350mm depth internal dimension, and provide a 50mm diameter water outlet hole provided with trap and screener, 100mm concrete partition wall between one wash basin to another same for slab. Top-level of wash basin from floor is 750mm, it will be casted on top of brick wall, includes formworks, bottle trap, drainers and necessary accessories; ( it will be used as hand wash basin as well) | m3 | 3.7 | 0 |  |  | 0.7
[7 empty] | 0.7 | 0
| Total Dhobi Sinks |  |  | 0 |  |  | 0.7 | 0
| TOTAL PLUMBING AND SANITARY ISTALLATION |  |  | 0
SUB SUMMARY - TOILET
| Foundation and walling |  |  | 0
| Roof structure |  |  | 0
| Total Dhobi Sinks |  |  | 0
| Finishing |  |  | 0
| Plumbing and Sanitary Installation |  |  | 0
| SUM TOILET AND LAUNDRY |  |  | 0
8 | WATER TOWER
A | Site cleance and excavation of foundations | m3 | 13 | 0
B | Masonry foundation wall | m2 | 46 | 0
C | 300mm thick Walling with fired bricks | m2 | 140 | 0
D | Supply and cast concrete grade 15 for oversite concrete | m2 | 28 | 0
E | RC concrete beams 4Y12 main bars, Y8-200c/c stirups, formworks | m3 | 1 | 0
F | RC concrete beams 4Y16 main bars, Y8-200c/c stirups, formworks. | M3 | 0.44 | 0
G | RC conrete roof slab mix ratio 1:2:4, Y12-175 c/c- use cement 42.5Nmm2 , formworks | m3 | 1.29 | 0
H | Construct four (4) reinforced concrete columns, column footings 4Y12 main bars, Y8-200c/c stirups, formworks. | m3 | 3 | 0
I | Plastering and skiming with lime ( optional) | m2 | 35 | 0
J | Painting ( optional) | m2 | 35 | 0
K | Supply and install 1000x2500 metal door with all accessories including padlocks for the store. | Nos | 1 | 0
L | Supply and install a sim tanks of 10,000 litres at top of the tower | Nos | 1 | 0
M | Supply and install a sim tanks of 5,000 litres at ground build foundation base | Nos | 1 | 0
| TOTAL WATER TOWER |  |  | 0
9 | INCINERATOR
A | Excavations | m3 | 2.5 | 0
B | Masonry stone foundation wall , motar 1:3 cement sand | m3 | 2.03 | 0
C | Fired brick 230mm walls 980x780mm internally by | m2 | 9.152 | 0
D | concrete grade 20 (1:2:4) reinforced 6mm BRC | m3 | 0.254 | 0
E | Reinforcement Y16 for burning platform | Kgs | 36.4 | 0
F | 150mm thick fired brick walls for 4.6m chimney jointed with cement mortar 1:3 | m2 | 4.214 | 0
Finishing
G | Pointing works and Panting works to ring beam surface color to be directed by the clien | m2 | 19.5 | 0
H | W3 - 400x400mm metal window for collecting ashes and inserting fuel into a burning chamber | Nos | 1 | 0
I | W4 - 300X300mm waste inlet window | Nos | 1 | 0
| TOTAL INCINERATOR |  |  | 0
GENERAL SUMMARY
| SUM TOILET AND LAUNDRY |  |  | 0
| TOTAL WATER TOWER |  |  | 0
| TOTAL INCINERATOR |  |  | 0
| SUM |  |  | 0
| CONTIGENCY 10% |  |  | 0
| VAT 18% |  |  | 0
| GRAND SUM 84 GIRL'S DORMITORY |  |  | 0

## WASH FACILITIES- Mwanga sec
Bill of Quantities For the Construction of water tank raiser, incinerator renovation, and renovation of hand wash sinks at Mwanga Secondary School - Kasulu TC
TOILETS
1 | Foundation and walling
Note: | The Contractor shall be deemed to have visited the site and satisfied himself as to:- The nature of the site, The amount of bush, rubbish or debris to be cleared away before commencement, access to the site, availability of materials and the like. All the cost is for contractor |  | NA | NA | NA
[8 empty] | 0.7 | 0
[8 empty] | 0.7 | 0
2 | Roof structure | [6 empty] | 0.7 | 0
A | Truss Fabrication and Installation • Materials: Supply well-seasoned and treated timber. Timber sections to be used:  Rafters: 50x150 mm. - eucaliptus  Tie beams: 50x150 mm. eucaliptus  Wall plates and struts: 50x100 mm. eucaliptus  Purlins: 50x70 mm. - Pine soft wood timber • Fabrication: Fabricate the trusses as per the provided drawings. Ensure the trusses are fabricated with a rafter slope of 8 degrees. • Installation: Install the fabricated trusses on the ring beam with a spacing of 1.4 meters center-to-center (c/c). Anchor the trusses to the ring beam using core M6 steel bars casted in the ring beam. Use two bolts (12mm diameter) with nuts and 2inches diameter washers to secure the joints of rafters and tie beams. • Overhangs: o The external overhang is to be 1.5 meters long. o The internal overhang at the hallway is to be 0.8 meters long. • Additional Provisions: o All tools, nails, and materials necessary for the truss fabrication and installation are to be included | Nos | 7 |  | 0 | 0.6 | 4.2
H | IT5 colorless but not trasperant covering sheets, fixed on streated pine timber purlins with roofing nails of 3.5 inches length | m2 | 137 |  | 0 |  |  | 0.7
I | Fascia board: treated pine timber - 25x200mm. Weld brackets at 600mm c/c | m2 | 30.1 |  | 0 |  |  | 0.7
[5 empty] | 0 |  |  | 0.7 | 0
| TOTAL ROOFING |  |  |  | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
3 | RC Concrete dhobi sinks, with terrazzo finishing |  |  |  | 0 |  |  | 0.7 | 0
A | Construct a (1:2:4) 6mm BRC reinforced concrete wash basin with a 600mm x 400mm width by 350mm depth internal dimension, and provide a 50mm diameter water outlet hole provided with trap and screener, 100mm concrete partition wall between one wash basin to another same for slab. Top-level of wash basin from floor is 750mm, it will be casted on top of brick wall, includes formworks, bottle trap, drainers and necessary accessories; ( it will be used as hand wash basin as well) | m3 | 1.7 |  | 0 |  |  | 0.7
[8 empty] | 0.7 | 0
| TOTAL DHOBI SINKS |  |  |  | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
4 | DOORS | [6 empty] | 0.7 | 0
[8 empty] | 0.7 | 0
| Supply and fix Door frames: Hardwood mininga or other equal and approved hardwood. Provide 16mm diameter burglar bars 150mm c/c , fix perforated 5mm thick clear sheet glass glazed to hardwood frame with glazing beads and fix a clear mosiquito wire net to prevent dust ant insects. | [6 empty] | 0.7 | 0
D | Ditto 850x2800mm high | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
[8 empty] | 0.7 | 0
| TOTAL DOORS |  |  |  | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
5 | Windows | [6 empty] | 0.7 | 0
[8 empty] | 0.7 | 0
A | Ditto1000x600 High ( Toilet) | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
[8 empty] | 0.7 | 0
| TOTAL WINDOW |  |  |  | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
6 | Finishing | [6 empty] | 0.7 | 0
A | Plastering 25mm thick 1:3 cement sand to foundation wall and to internal walls | m2 | 85.2 |  | 0 |  |  | 0.7 | 59.64
B | waterproof plastering 1:4 in toilets plus skimmed gley cement pigment. Ditto for wall above wash basin. | m2 | 42.4 |  | 0 |  |  | 0.7 | 29.68
C | Terrazo floor finishing | m2 | 63.5 |  | 0 |  |  | 0.7 | 44.45
D | Vanish exernal ISSB wall | m2 | 0 |  | 0 |  |  | 0.7 | 0
E | Painting three coats of bituminous paint to the foundation walls, silk Paint to internal walls , weather guard paint to external walls, and painting to fascia board | m2 | 45 |  | 0 |  |  | 0.7 | 31.5
[8 empty] | 0.7 | 0
| TOTAL FINISHING |  |  |  | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
7 | Plumbing and Sanitary Installation | [6 empty] | 0.7 | 0
| Supply and fix ; | [6 empty] | 0.7 | 0
A | Wash hand basins; white vitreous China; 32mm chromium plated chain waste 32mm plastic bottle trap concealed bracket with fixing clamps pair 12mm pillar taps 420 x 510mm; requiring plugging. fixing with brass screws to backgrounds ( install at changing/women's room and at disabled toilet room) | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
B | Squatting -White vitreous asian type W.C suite comprising 9 litres capacity cistern with cover, 12mm BSS high pressure ball valve, plastic syphon fitting, side supply and overflow set | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
D | 80mm Diameter high quality plastic floor drain trap built in concrete bed | Nos | 6 |  | 0 |  |  | 0.7 | 4.2
E | 6mm silver mirror, lead backed, size 450 x600mm with arise edges fixed to wall with mirror screws | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
H | Shurtuff (Douche spray) 13mm diameter X 1000mm long flexible hose metal braided hose | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
I | [7 empty] | 0.7 | 0
J | Pipes work in building | [6 empty] | 0.7 | 0
K | A: Supply pipe PN 16 | [6 empty] | 0.7 | 0
L | 25mmØ communication pipe HDPE to trench | m | 16 |  | 0 |  |  | 0.7 | 11.2
M | Ditto; tee | Nos | 6 |  | 0 |  |  | 0.7 | 4.2
N | Ditto; elbow | Nos | 9 |  | 0 |  |  | 0.7 | 6.3
O | Ditto; male connector | Nos | 6 |  | 0 |  |  | 0.7 | 4.2
P | 32mmØ pipe to trench | Nos | 6 |  | 0 |  |  | 0.7 | 4.2
Q | Ditto; elbow | Nos | 3 |  | 0 |  |  | 0.7 | 2.1
R | Ditto; nipple MM | Nos | 9 |  | 0 |  |  | 0.7 | 6.3
S | Ditto; nipple FF | Nos | 9 |  | 0 |  |  | 0.7 | 6.3
T | Ditto; union | Nos | 6 |  | 0 |  |  | 0.7 | 4.2
U | Ditto; reducing connector 32Ø × 25Ø | Nos | 9 |  | 0 |  |  | 0.7 | 6.3
V | Ditto; reducing connector 25Ø × 19Ø | Nos | 9 |  | 0 |  |  | 0.7 | 6.3
W | Ditto; nipple MM | Nos | 9 |  | 0 |  |  | 0.7 | 6.3
X | Ditto; reducing connector 19Ø × 13Ø | Nos | 9 |  | 0 |  |  | 0.7 | 6.3
Y | 13mm diameter pipe in blockwall chase BS 1010 or 1212 | m | 15 |  | 0 |  |  | 0.7 | 10.5
Z | Ditto; elbow | Nos | 18 |  | 0 |  |  | 0.7 | 12.6
AA | Ditto; tee. | Nos | 10 |  | 0 |  |  | 0.7 | 7
AB | Ditto: nipple MM | Nos | 10 |  | 0 |  |  | 0.7 | 7
AC | Ditto: nipple FF | Nos | 1 |  | 0 |  |  | 0.7 | 0.7
AD | Ditto: union | Nos | 10 |  | 0 |  |  | 0.7 | 7
[8 empty] | 0.7 | 0
| B: WASTE AND VENT PIPES | [6 empty] | 0.7 | 0
| UPVC pipes: class 'C' | [6 empty] | 0.7 | 0
AE | 38mmØ; chase in block in concrete slab. | m | 5 |  | 0 |  |  | 0.7 | 3.5
AF | Ditto: Equal tee | Nos | 5 |  | 0 |  |  | 0.7 | 3.5
AG | Ditto; plain elbow | Nos | 3 |  | 0 |  |  | 0.7 | 2.1
AH | Ditto; plugged elbow |  | 3 |  | 0 |  |  | 0.7 | 2.1
[8 empty] | 0.7 | 0
AI | C: SOIL AND PIPES | [6 empty] | 0.7 | 0
AJ | UPVC pipes and fittings: Class 'C' | [6 empty] | 0.7 | 0
AK | 100mmØ pipe fixed to walls | m | 9 |  | 0 |  |  | 0.7 | 6.3
AL | Ditto; laid in trenches. | m | 32 |  | 0 |  |  | 0.7 | 22.4
AM | Ditto; plugged bend 90˚. | Nos | 5 |  | 0 |  |  | 0.7 | 3.5
AN | Ditto; plain bend 90˚. | Nos | 5 |  | 0 |  |  | 0.7 | 3.5
[8 empty] | 0.7 | 0
| D: Ancillaries: | [6 empty] | 0.7 | 0
| Draw off taps; stop valves; copper alloy to BS 5154 or BS 1010 | [6 empty] | 0.7 | 0
AO | 13mmØ stop valve | Nos | 10 |  | 0 |  |  | 0.7 | 7
AP | 13mm Ø bib taps Chrome plated | Nos | 10 |  | 0 |  |  | 0.7 | 7
AQ | 13mm angle valves | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
AR | Provision for wastebin for waste collection in the MHM room | Nos | 2 |  | 0 |  |  | 0.7 | 1.4
[8 empty] | 0.7 | 0
| FOUL WATER DRAINAGE | [6 empty] | 0.7 | 0
| MANHOLE AND GULLY TRAP | [6 empty] | 0.7 | 0
AS | Construct a masonry manhole size 600 x x600mm average depth 600mm with fired bricks, mortar ratio 1:3 | Nos | 4 |  | 0 |  |  | 0.7 | 2.8
[5 empty] | 0 |  |  | 0.7 | 0
[5 empty] | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
| TOTAL PLUMBING AND SANITARY ISTALLATION |  |  |  | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
8 | WATER TOWER | [6 empty] | 0.7 | 0
A | Site cleance and excavation of foundations | m3 | 13 |  | 0 |  |  | 0.7 | 9.1
B | Masonry foundation wall | m2 | 46 |  | 0 |  |  | 0.7 | 32.2
C | 300mm thick Walling with fired bricks | m2 | 140 |  | 0 |  |  | 0.7 | 98
D | Supply and cast concrete grade 15 for oversite concrete | m2 | 28 |  | 0 |  |  | 0.7 | 19.6
E | RC concrete beams 4Y12 main bars, Y8-200c/c stirups, formworks | m3 | 1 |  | 0 |  |  | 0.7 | 0.7
F | RC concrete beams 4Y16 main bars, Y8-200c/c stirups, formworks. | M3 | 0.44 |  | 0 |  |  | 0.7 | 0.308
G | RC conrete roof slab mix ratio 1:2:4, Y12-175 c/c- use cement 42.5Nmm2 , formworks | m3 | 1.29 |  | 0 |  |  | 0.7 | 0.903
H | Construct four (4) reinforced concrete columns, column footings 4Y12 main bars, Y8-200c/c stirups, formworks. | m3 | 3 |  | 0 |  |  | 0.7 | 2.1
I | Plastering and skiming with lime ( optional) | m2 | 35 |  | 0 |  |  | 0.7 | 24.5
J | Painting ( optional) | m2 | 35 |  | 0 |  |  | 0.7 | 24.5
K | Supply and install 1000x2500 metal door with all accessories including padlocks for the store. | Nos | 1 |  | 0 |  |  | 0.7 | 0.7
L | Supply and install a sim tanks of 10,000 litres | Nos | 1 |  | 0 |  |  | 0.7 | 0.7
M | Supply and install a sim tanks of 5,000 litres | Nos | 1 |  | 0 |  |  | 0.7 | 0.7
[8 empty] | 0.7 | 0
| TOTAL WATER TOWER |  |  |  | 0 |  |  | 0.7 | 0
[8 empty] | 0.7 | 0
9 | INCINERATOR | [6 empty] | 0.7 | 0
[8 empty] | 0.7 | 0
A | Excavations | m3 | 2.5 |  | 0 |  |  | 0.7 | 1.75
B | Masonry stone foundation wall , motar 1:3 cement sand | m3 | 2.03 |  | 0 |  |  | 0.7 | 1.421
C | Fired brick 230mm walls 980x780mm internally by | m2 | 9.152 |  | 0 |  |  | 0.7 | 6.4064
D | concrete grade 20 (1:2:4) reinforced with 6mm BRC | m3 | 0.254 |  | 0 |  |  | 0.7 | 0.1778
E | Reinforcement Y16 for burning platform | Kgs | 36.4 |  | 0 |  |  | 0.7 | 25.48
F | 150mm thick fired brick walls for 4.6m Chimney length jointed with cement mortar 1:3 | m2 | 4.214 |  | 0 |  |  | 0.7 | 2.9498
[8 empty] | 0.7 | 0
| Finishing | [6 empty] | 0.7 | 0
G | Pointing works and Panting works to ring beam surface color to be directed by the clien | m2 | 19.5 |  | 0 |  |  | 0.7 | 13.65
H | W3 - 400x400 metal window for incinarator | Nos | 1 |  | 0 |  |  | 0.7 | 0.7
I | W4 - 300X300 incinerator | Nos | 1 |  | 0 |  |  | 0.7 | 0.7
J | W5 - 150x150 Incinerator | Nos | 1 |  | 0 |  |  | 0.7 | 0.7
[8 empty] | 0.7 | 0
| TOTAL INCINERATOR |  |  |  | 0 |  |  |  | 0
GENERAL SUMMARY
| Foundation and walling |  |  |  | 0
| Roof structure |  |  |  | 0
| Dhobi sinks |  |  |  | 0
| Doors |  |  |  | 0
| windows |  |  |  | 0
| Finishing |  |  |  | 0
| Plumbing and Sanitary Installation |  |  |  | 0
| Water tower |  |  |  | 0
| Incinerator |  |  |  | 0
| SUM |  |  |  | 0
| CONTIGENCY 10% |  |  |  | 0
| VAT 18% |  |  |  | 0 |  |  |  |  | inT in dormitory | 91
[10 empty] | OuT for 25 school | 70.35
| GRAND SUM A WASH FOR GIRL'S |  |  |  | 0 |  |  |  |  | different | 20.65
[10 empty] | deduct | 0.29353